# Plan for Working with CMU TechSpark

How we get the physical piano's mechanical parts made. Based on the TechSpark services page: <https://engineering.cmu.edu/techspark/facilities/services.html>

## What TechSpark offers us

3D printers

| Printer | Process / material | Build volume | Min feature |
| --- | --- | --- | --- |
| Bambu X1C | FDM, PLA | 10 × 10 × 10″ (254 mm) | 0.4 mm |
| Stratasys F170 | FDM, ABS + soluble support | 10 × 10 × 10″ | 0.4 mm |
| Formlabs Form 3 | SLA resin (listed as coming soon) | 14.5 × 14.5 × 19.3 cm | 85 µm |

Materials & pricing: PLA $0.64/g · ABS $1.03/g · resin $1.08/g

Also available: machining, fabrication, welding, CNC, laser cutting, and CAD/file-prep help from staff. Professional services $65/hr + machining $72/hr or fabrication $74/hr.

File formats accepted: .stl .obj .3mf .zip

How jobs are submitted: through the FBS system at <https://cmu.fbs.io/>, after an in-person consult at Hamerschlag Hall C124. Billing is via a CMU oracle string / Andrew HUB account.

Contacts

•  3D printing & fabrication — Jen Hitchcock, jhitchco@andrew.cmu.edu

•  Machining — Ed Wojciechowski, wojo@andrew.cmu.edu

## The one hard constraint this creates

The keyboard is 545 mm wide; the build volume is 254 mm. The keybed cannot be printed as one piece. The CAD is already designed around this: the base is built from tileable 50 mm cells, so we print it in runs and join them.

•  5 cells per tile = 250 mm → fits the 254 mm bed with 4 mm to spare.

•  11 keys = 3 tiles (5 + 5 + 1), joined with M3 hardware.

•  Individual white keys (140 × 45 mm) and black keys (87 × 26 mm) fit easily and can be batched many-per-plate.

## Proposed plan

### Phase 1 — Consult (before printing anything)

Go to HH C124 and talk to Jen Hitchcock. Bring the CAD and these questions:

1.  Tolerances for moving parts. Our design has a pin hinge and a sliding plunger with 0.4 mm clearances. Is that achievable on the X1C in PLA, or should we open it up? (This is the single most important question — the whole mechanism depends on the key pivoting freely without slop.)

2.  PLA vs. ABS. PLA is cheapest. The F170's soluble support could print the hinge better. Is ABS worth the 1.6× material cost here?

3.  Laser-cut the switch plate instead of printing tiles. ⭐ Highest-value question. MX switches are plate-mount: they clip into a flat plate with 14 × 14 mm square holes. Cutting that as one piece would:

4.  hold all 11 switches at an exact 50 mm pitch with no tile seams — the arm's calibration depends on that pitch, so this removes a real risk, not just a cost;

5.  likely fit the laser bed in one piece (545 mm) where the 254 mm print bed cannot;

6.  reduce printed mass from ~502 g to ~275 g ($321 → ~$176). Note the saving is modest, not half: laser machine time is billed hourly and isn't quoted on the services page, so net saving is likely $30–80. Ask what laser time actually costs — it decides whether the cost argument holds at all. The pitch accuracy above is the real reason.

A worked layered design already exists at    `../cad/piano_base_laser.scad`: four flat layers    (base / spacer / switch plate / stop rail) whose thicknesses land the switch    plate at z=12 mm and the stop at z=25 mm — identical to the printed version,    so key height and arm height are unchanged. Only 22 small hinge blocks stay    printed, because they need a cross-drilled pin hole a laser can't make.

Specifics to confirm: can the bed take 545 mm, and can they supply    ~1.5 mm stock (the thickness MX switches clip into)? If 1.5 mm is too    flimsy over that span, is a stepped two-layer plate (1.5 mm with 14 mm holes    over a thicker backing with clearance holes) feasible?

1.  Tile joining. The base cells now carry alignment dowel half-holes on every edge, so a tile seam closes onto a 3 mm rod rather than being butted by eye. Worth asking whether they would also glue or pin the seam, since the 50 mm key pitch — what the arm is calibrated to — has to survive two joins on this route. This is now the likely route, so it deserves more attention than the laser alternative.

2.  Turnaround time and how billing works against our lab's oracle string.

### Phase 2 — Prototype ONE key

Print 1 white key + 1 base cell + 1 black key (~$30 of material) and check:

•  Does the key pivot freely and return cleanly?

•  Does the switch actuate before the cap hits the bottom stops?

•  Do the robot's fingers land in the front clear zone (see below)?

•  Is the key-top height reachable by the arm's vertical adjustment?

Do not batch 11 until this passes. Tuning a parameter costs one reprint at this stage and eleven reprints later.

### Phase 3 — Full run

Once the prototype is signed off, submit:

•  11 × white key lever

•  3 × base tile (5 + 5 + 1 cells, with black-key grooves at the right indices) — or the laser-cut plate stack, if consult question 3 is a yes

•  7 × black key

⚠️ Specify low infill (~20%) on the key levers. This is a functional requirement with a hard number: the switch datasheet guarantees only 15 gf of return force, so the maximum safe key mass is 24 g. A near-solid key at ~41 g would press its own switch and self-trigger. At ~20% infill (~16 g) there is a 1.5× margin. It is also cheaper, since TechSpark bills by the gram.

### Phase 4 — Assembly & integration

Wire the switches to the Arduino, flash the firmware, tune the tones, then set the arm height so the resting fingertips hover 2–5 mm above the key tops, and re-run the demo sequence.

## Parts manifest — what is made how

⚠️ The CAD files are split by ROUTE, not by process. piano_base_laser.scad is the laser route — it still contains one 3D-printed part. And either route needs `piano_keys.scad`, because the key levers and black keys are printed in both. Do not hand over a single file and assume it covers everything.

Route A — all 3D printed

| Part | File | mode | Process | Qty |
| --- | --- | --- | --- | --- |
| Key lever (notched for the black keys) | piano_keys.scad | "key" | print, PLA ~20% infill | 11 |
| Black key (switched keycap) | piano_keys.scad | "black" | print | 7 |
| Base tile (5 cells) | piano_base_printed.scad | "tile" | print | 3 (5+5+1) |
| Frame cheek | piano_frame.scad | "cheek" | print | 2 |
| Frame front rail segment | piano_frame.scad | "front_seg" | print | 3 |
| Frame back rail segment | piano_frame.scad | "back_seg" | print | 3 |
| Hinge pin | — | — | buy 3 mm rod, cut | — |
| Tile alignment dowels | — | — | same 3 mm rod, 4 short pieces | — |

Feet are printed into every base cell, so this route needs no standoffs.

Route B — laser-cut base (the one we're asking about)

| Part | File | mode | Process | Qty |
| --- | --- | --- | --- | --- |
| Key lever | piano_keys.scad | "key" | print | 11 |
| Black key | piano_keys.scad | "black" | print | 7 |
| Structure sheet | piano_base_laser.scad | "2d_struct" | laser, 9 mm | 1 |
| Switch plate | piano_base_laser.scad | "2d_switch_plate" | laser, 1.5 mm | 1 |
| Stop rail | piano_base_laser.scad | "2d_stop_rail" | laser, 13 mm | 1 |
| Hinge bracket | piano_base_laser.scad | "hinge_block" | print | 12 |
| Hinge pin | — | — | buy 3 mm rod, ~570 mm | 1 |
| Standoffs | — | — | buy, 12 mm M3 | 6 |

So Route B is 3 laser parts + 30 printed parts, drawn from two files.

## What to send them

•  Laser: ../cad/piano_base_laser.scad exported to DXF — one file per 2d_* mode (3 files), each tagged with its stock thickness.

•  Print: STL per part — key lever and black key (piano_keys.scad), plus either the base tiles (piano_base_printed.scad) or the hinge bracket (piano_base_laser.scad).

•  This document, for the manifest, build volumes, and material context.

We don't have OpenSCAD on the lab PC yet — it's a free download, or TechSpark staff can help with file prep as part of professional services.

## Design status

✅ Black-key clearance — resolved. Black keys occupy the rear 62% of each key, so fingers must press in the front 53.2 mm. Measured on the rig: the fingertip lands 35 mm from the front edge. Comfortably clear, no repositioning needed.

⏳ Base construction — depends on consult question 3. If laser-cutting the switch plate is approved, the base is redesigned from printed 50 mm cells into a stack of flat laser-cut layers, and only the key levers and black keys stay 3D printed. Do not start that rework until TechSpark confirms bed size and material — and do not commit to the printed-tile base until question 3 is answered either way.